## DIPH Feasibility study - Plan for scoping visit

**Aims of the scoping visit:**

1. At the zonal level to establish which woreda (district) offices will be the in the feasibility study.
2. At the zonal level to establish which private health facilities will be in the feasibility study.
3. At the woreda level to establish which health centers and health posts will be in the feasibility study.
4. At the woreda level to establish which private health facilities will be in the feasibility study.
5. At the woreda level to establish which NGO will be in the feasibility study.
6. To establish a schedule for the feasibility study
7. To introduce the project to key contact persons in the zone and woreda offices and facilities.
8. To set appropriate time and date for the feasibility study with the identified key contact persons.
9. To establish travel route for the feasibility study.
10. To establish accommodation where necessary.

Proposed regions, zones and woredas (districts) for DEP scoping and feasibility study

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Region** | **Zone** | **Name** | **Estimated Distance from Addis** | **Number of days required** |
|  |
| Oromiya | West Showa |  |  | 3 |
|  |  |
| Amhara | North Showa |  |  | 4 |
|  |  |

In selecting the woredas we took into consideration the following:

* Language: we ensured that language would not be a barrier.
* Accessibility: woredas had to be accessible by vehicle.
* Grantee presence.
* Proximity: preference was given to woredas that were closer to the capital, Addis Ababa.